## Project Overview
Project : Dumaru Bhawan
Start Date : 2020-11-26
Expected Completion Date : 2021-04-30
Project Manager : Sundar Machamasi (Developer, Designer, QA)
Admin Template : Otika Admin Dashboard template
Front End Template : Corlate
Programming Language : PHP
Helper language : css, html, javascript, jquery, ajax
Database : Mysql Database
DB name : db_dumaru
username : root
password :
S.No. | Division | Task | Start Date | End Date | Responsible | Result | Remark
1 | Admin | Design Static Login Page | 2020-11-26 | 2020-11-26 | Sundar | OK
2 | Admin | Make login page dynamic and functional. | 2020-11-26 | 2020-11-26 | Sundar | OK
3 | Admin | Create Admin Panel | 2020-11-26 | 2020-11-26 | Sundar | OK
4 | Admin | Create Static User Management Layout | 2020-11-27 | 2020-11-27 | Sundar | OK
5 | Admin

## AdminLoginLayout
1 | Admin Login Page Layout

## DashboardLayout
Division: Admin
Page : Dashboard
Date: 2020/11/27
Programmer : Sundar Machamasi

## UserMgmtLayout
Division: Admin
Page : User Module
Date: 2020/11/27
Programmer : Sundar Machamasi
1 | List User Page(Static Only but functional)

## DB_TABLE
Title : List of tables used in DumaruBhawan
Created Date : 2020-11-27
Created By : Sundar
Database Name : db_dumaru
username : root
password :
S.No | Table Name | No. of Column | PK | FK | Comment | Remark
1 | tbl_login | 5 | login_id | user_id, role_id |  | FK is not adjusted yet. Will use in future if needed.
2

## tbl_login
Title : Login Table besic design
Created by : Sundar Machamasi
Created on : 2020-11-26
Updated by:
Updated on:
Table name : tbl_login
S.No. | Column Name | Physical Name | Data Type | Length | Null | Extra | Comment | Remark
1 | id | Login Id | int | 11 | NO | AI | Primary Key
2 | username | User Name | String | 25 | NO
3 | password | User Password | String | 55 | NO
4 | user_id | User Id | int | 11 | NO |  |  | Foreign Key with User Id in user table
5 | role_id | User Role Id | tinyint | 2 | NO

## tbl_users
Title : Login Table besic design
Created by : Sundar Machamasi
Created on : 2020-11-27
Updated by:
Updated on:
Table name : tbl_users
S.No. | Column Name | Physical Name | Data Type | Length | Null | Default | Extra | Comment | Remark
1 | id | User id | int | 11 | NO |  | AI | Primary Key
2 | firstname | First Name | String | 55 | NO
3 | lastname | Last Name | String | 55 | NO
4 | username | Username | String | 25 | NO
5 | password | Password | String | 100 | NO
6 | email | Email | String | 55 | Yes
7 | dob | Date of Birth | Date |  | Yes
8 | gender | Gender | String | 25 | Yes
9 | address | Address | String | 255 | Yes
10 | contact_no | Contact no | String | 25 | Yes
11 | details | Client Details | Text |  | Yes
12 | created_on | Create Date | datetime |  | Yes
13 | created_by | Create By | int | 2 | Yes
14 | modified_on | Modified Date | datetime |  | Yes
15 | modified_by | Modified By | int | 2 | Yes
16 | del_flag | Delete flag | tinyint | 1 | Yes | 0 |  | 0:ON 1:OFF
17 | status | User Status | tinyint | 1 | Yes | 1 |  | 1:Active 0:Inactive
18 | role_id | User role | int | 2 | Yes |  |  | FK | Foreign Key with Role Id in Role table